## Initial
Project Plan: 2D RPG Game with UNITY by Sasha Stepanov
Phase | Activity | Estimated Time (hrs) | Due Date | Actual Time (hrs) | Actual Date | Variance (hrs)
Discovery | Client Interview | 1 |  | 1 |  | 0
| Define Objectives and Goals | 0.5 |  | 0.5 |  | 0
| Target audience | 0.1 |  | 0.1 |  | 0
| Information gathering report | 5 |  | 6 |  | 1
| Proposal/Vison Statement | 4 |  | 6 |  | 2
| Risk Analysis | 2 |  | 1 |  | -1
| Plan | 2 |  | 3 |  | 1
Exploration
| Specifications | 10 |  | 15 |  | 5
| Initial storyboard | 2 |  | 2.5
| Further refined storyboard | 0.5 |  | 1
| Completed storyboard | 2 |  | 3
Refinement | Test prototype | 20
| Testing of prototype | 5
| Refinement of prototype | 10
Production | A production of the prototype | 30 |  |  |  |  | Prototype is a game with some minimum action involved
| Creating a tiles/maps | 10
| Game Production (player,boss,shops,items) | 25
| User Testing | 2
| Product changes/polish | 5
Implementation | User testing | 2
| Changes made | 3
| Client presentation | 0.5
| Product delivered | 1
| Product goes live | 1
| total time | 143.6 |  | 39.1 | Total Variance | 8