## Final
Project Plan: Virtual Tour - Mikael Christensen .v2
Phase | Activity | Estimated Time (hrs) | Due Date | Actual Time (hrs) | Actual Date | Variance (hrs)
Discovery | Client Interview | 1 | 2019-08-09 | 0.7 | 2019-08-16 | -0.3 | Interview delayed
| Define Objectives | 0.2 | 2019-08-09 | 0.15 | 2019-08-16 | -0.05
| Define Goals | 0.2 | 2019-08-09 | 0.15 | 2019-08-16 | -0.05
| Target audience | 0.1 | 2019-08-09 | 0.1 | 2019-08-16 | 0
| Information gathering report | 2 | 2019-08-16 | 1.6 | 2019-08-23 | -0.4
| Proposal/Vison Statement | 3 | 2019-08-16 | 3.5 | 2019-08-23 | 0.5
| Risk Analysis | 2 | 2019-08-23 | 2 | 2019-08-29 | 0
| Plan | 2 | 2019-08-29 | 2.5 | 2019-08-29 | 0.5
Exploration | Image capture/gathering | 5 | 2019-09-06 | 3 | 2019-10-06 | -2 | Image gathering is delayed due to equipment issues
| Specifications | 4.5 | 2019-09-13 | 5.5 | 2019-09-17 | 1
| Initial storyboard | 4 | 2019-09-20 | 4 | 2019-09-24 | 0
| Further refined storyboard | 2 | 2019-09-20 | 2 | 2019-09-28 | 0
| Completed storyboard | 3 | 2019-09-27 | 2 | 2019-10-03 | -1
Refinement | Test prototype of Lapentor | 20 | 2019-10-04 | 22 | 2019-10-04 | 2
| Additional Image Gathering | 2 | 2019-10-11 | 2 | 2019-10-11 | 0
| Testing of prototype | 5 | 2019-10-11 | 2 | 2019-10-11 | -3
| Testing Functionality | 5 | 2019-10-11 | 3.5 | 2019-10-11 | -1.5
| Usability Testing Plan | 3 | 2019-10-11 | 3 | 2019-10-11 | 0
| Refinement of prototype | 10 | 2019-10-18 | 10 | 18/20/2019 | 0
Production | A production of the prototype | 25 | 2019-10-25 | 22 | 2019-10-29 | -3
| User Testing | 2 | 2019-10-25 | 2 | 2019-10-29 | 0
| Product changes/polish | 5 | 2019-10-25 | 4 | 2019-10-29 | -1
| Additonal Image Gathering | 1 | 2019-10-25 | 1 | 2019-10-29 | 0
| Prototype Handin | 1 | 2019-11-01 | 1 | 2019-11-01 | 0
| Client presentation | 1 | 2019-11-01 | 1 | 2019-11-01 | 0
Implementation | User testing | 3 | 2019-11-08 | 3 | 2019-11-05 | 0
| Changes Made | 5 | 2019-11-22 | 6 | 2019-11-22 | 1
| Product delivered | 1 | 2019-11-22 | 1 | 2019-11-22 | 0
| Product goes live | 1 | 2019-11-22 | 1 | 2019-11-22 | 0
| total time | 119 |  | 111.7 | Total Variance | -7.3

## Initial
Project Plan: Virtual Tour - Mikael Christensen .v1
Phase | Activity | Estimated Time (hrs) | Due Date | Actual Time (hrs) | Actual Date | Variance (hrs)
Discovery | Client Interview | 1 | 2019-08-09 | 0.7 | 2019-08-16 | -0.3 | Interview delayed
| Define Objectives | 0.2 | 2019-08-09 | 0.15 | 2019-08-16 | -0.05
| Define Goals | 0.2 | 2019-08-09 | 0.15 | 2019-08-16 | -0.05
| Target audience | 0.1 | 2019-08-09 | 0.1 | 2019-08-16 | 0
| Information gathering report | 2 | 2019-08-16 | 1.6 | 2019-08-23 | -0.4
| Proposal/Vison Statement | 3 | 2019-08-16 | 3.5 | 2019-08-23 | 0.5
| Risk Analysis | 2 | 2019-08-23 | 0.5 | 2019-08-29 | -1.5
| Plan | 2 | 2019-08-29 | 2.5 | 2019-08-29 | 0.5
Exploration | Image capture/gathering | 5 | 2019-09-06 | 3 | 2019-10-06 | -2 | Image gathering is delayed due to equipment issues
| Specifications | 4.5
| Initial storyboard | 4
| Further refined storyboard | 2
| Completed storyboard | 3
Refinement | Test prototype of Lapentor | 20
| Testing of prototype | 5
| Refinement of prototype | 10
Production | A production of the prototype | 25
| Website production | 15
| User Testing | 2
| Product changes/polish | 5
Implementation | User testing | 2
| Changes made | 4
| Client presentation | 1
| Product delivered | 1
| Product goes live | 1
| total time | 120 |  | 12.2 | Total Variance | -3.3